## 1st
S.No | Product | Customer | Item Description | QA feature Status | Open issues | Closed issues | Resource | Development Status | QA Resource
1 | LIMS | Bansal | The Default branch option once login should not come even after save clicked | Working |  |  | Senthil D | Yet to Start | Given
2 | LIMS | Bansal | MIS Report Link has to be removed from Main Link | Working with issues | 13181- High |  | Senthil D | Yet to Start | Given
3 | LIMS | Bansal | Calendar control instead of the current control in the MIS reports | Working |  |  | Senthil D | Yet to Start | Given
4 | LIMS | Bansal | Discount MIS Report - Gross amount is not shown properly. It is Showing wrong data | Not working | 13180- Critical |  | Saravanan | Yet to Start | Given
5 | LIMS | CDC | OUTSTANDINGREPORT-Export to pdf option required | Working |  | 13163- Critical, | Babu | Completed | Given
6 | LIMS | Dar Al Hikmah | Invoice new format (DAH has to provide the format)..Invoice format need to be changed as per given format | Working |  | 13168- Medium, 13169- Critical | Arun P | Completed | Given
7 | LIMS | Labcorp | In Technician, Authorisation & Dispatch Role- Filter Required Time wise based on registration | Not working | 13166- High, 13167- high | 13165- medium, | Arun P | Completed | Given
8 | LIMS | Makashir | "Need following columns in Home Collection Charges Report 1. Gross Amount 2. Discount Amount 3. Net Amount 4. Due Amount 5. Area 6. Due Clear Date Add filter on the top for Due Clear Date as well" | Not working | 13170- Low, 13171- Critical, 13172- Critical, 13173- Critical, 13174- High, 13176- Critical |  | Babu | Completed | Given
9 | LIMS | Makashir | Need the ability to download the Home Collection Charges Report (both Summary and Detail tabs) to PDF and Excel. The exported data should with the filters applied. | Working with issues | 13175- high |  | Babu | Completed | Given
10 | LIMS | Makashir | While creating a direct GRN, the price of the items which is entered in the master data should be non-editable. However, sometimes the actual price the items come at ,can vary (near-expiry discount, promotional discount, price hike etc.). So the person who receives the goods should be able to enter the actual price the goods came at also. On the GRN PDF, I would like to see both prices for each item - the price in the master data and the actual price the item came at. Similarly, I want to see these both prices on the GRN Tracking screen as well. | Working with issues | 13182- Critical, 13183- Critical |  | Babu | Inprogress | Given
11 | LIMS | Trident | PHC MIS report need to add few more group test same as the existing excel format-Groups are LFT,TFT and HBA1C-Format has been shared in mail | Working with issues | 13178- Medium 13179- Medium |  | Saravanan | Inprogress | Given
12 | LIMS | Dar Al Hikmah | External VisitID needs to show in Transaction Detail MIS Report | Working with issues | Bug1.: External visit iD header is showing duplicates in excel sheet Bug2:. External visit id details are not showing in the PDF |  | Prasana | Completed | Given
13 | LIMS | DDC | Service Quantity needs to show in Transaction Detail MIS Report | Working with issues | Bug1. Service Quantity details are shown for grand total column also |  | Prasana | Completed | Given
14 | LIMS | All | Normal work flow | Normal | 13164- Medium, 13177- High, Bug1.: Due Patient not shoiwng in the Due clearnce screen by defuly after serching ionly its showing |  |  |  | Given

## 2nd
Product | Customer | Item Description | QA status | Open Bug IDs | QA resource | Resource
LIMS | Bansal | The Default branch option once login should not come even after save clicked | Working |  | Sajan | Senthil D
LIMS | Bansal | MIS Report Link has to be removed from Main Link | Working with issues | 13181- High | Sajan | Senthil D
LIMS | Bansal | Calendar control instead of the current control in the MIS reports | Working |  | Sajan | Senthil D
LIMS | Bansal | Discount MIS Report - Gross amount is not shown properly. It is Showing wrong data | Working with issues | 13180- High | Sajan | Saravanan
LIMS | Makashir | While creating a direct GRN, the price of the items which is entered in the master data should be non-editable. However, sometimes the actual price the items come at ,can vary (near-expiry discount, promotional discount, price hike etc.). So the person who receives the goods should be able to enter the actual price the goods came at also. On the GRN PDF, I would like to see both prices for each item - the price in the master data and the actual price the item came at. Similarly, I want to see these both prices on the GRN Tracking screen as well. | Not Working | 13182- Critical, 13183- Critical | Sajan | Babu
LIMS | Trident | PHC MIS report need to add few more group test same as the existing excel format-Groups are LFT,TFT and HBA1C-Format has been shared in mail | Working with issues | 13178- Medium, 13179- Medium | Sajan | Saravanan
LIMS | Dar Al Hikmah | External VisitID needs to show in Transaction Detail MIS Report | Working with issues | 13183- High, 13184- High | Sajan | Prasana
LIMS | DDC | Service Quantity needs to show in Transaction Detail MIS Report | Working with issues | 13185- Medium | Sajan | Prasana
LIMS | All | Normal work flow | Normal | 13186-High | Sajan | All
Product | Customer | Item Description | QA status | Resolvled Bug IDs | QA resource | Resource
LIMS | Dar Al Hikmah | Invoice new format (DAH has to provide the format)..Invoice format need to be changed as per given format | Done | 13168- Closed, 13169(Not an issue)- Closed | Sajan | Arun P
LIMS | Labcorp | In Technician, Authorisation & Dispatch Role- Filter Required Time wise based on registration | Done | 13165-Closed, 13166-reopen, 13167- reopen | Sajan | Arun P

## 3rd
Customer | Item Description | QA status | Open Bug IDs | QA Resource | Resource
Bansal | Page 2 is not loading when record is saved in page 2 on reloading page 1 gets loaded in Result Entry Patient List | Working With issue | 13187- High, 13188- High | Sajan | Arun P
Bansal | When complete option is clicked in the Bulk entry list, only the first page complete records are shown it has to show overall complete records not only first page completed records | Working |  | Sajan | Arun P
Bansal | Thyroid has to be both Numeric and Text as some data will come with < or > symbol, delta has to be introduced for this cases as well. | Working With issue | 13189- High, 13190- High | Sajan | Arun P
Bansal | Bill No or Branch Code column in the Bulk Entry List and Bulk Entry Screen | Not wokring | 13191- Critical, 13192- Critical, 13193- Low | Sajan | Arun P
Bansal | Sorting option Name, VisitID, doctor name in Service wise Transaction report | Working With issue | 13194- High | Sajan | Prasana
Bansal | In User wise report collection report - Previous Due Amount break up is needed ( Format provided ) | Working With issue | 13195- High | Sajan | Babu
Bansal | On Click of the Visit ID for each patient, the service details has to be shown in Outstanding Report | Working | 13196- Medium | Sajan | Arun P

## 4th
Product | Customer | Item Description | Feature Status | Open Bug IDs | QA Resource | Resource
LIMS | Bansal | Report Generated on 05/02/2020 - Rename to Report Date 05/02/2020 | Not Working | 13197-High, 13198- Critical, 13199-Critical | Sajan | Prasana
LIMS | Bansal | Discount Report should have same structure/format like Outstanding report | Not Working | 13205- Critical, 13206-High | Sajan | Babu
LIMS | Bansal | Discount MIS Report, Advanced Transaction MIS Report, User MIS Report, Collection MIS Reports, Service Wise Summary MIS Report. | Not Working | 13199-Critical, 13200- Critical, 13201- High, 13202- Critical, 132003- Critical, 13204- High, | Sajan | Suresh

## 5th
Customer | Item Description | Feature Status | Open Bug IDs | QA Resource | Resource
Bansal | Label Printing at both test level and department level in Patient list and dispatch | Partially tested | 13207- High | sajan | Senthil D
Bansal | Comprehensive Status Report - Sample collected should not show for Radiology - "InProcess" | Not Working | 13208- Critical | sajan | Dinesh
Bansal | Sort the report based on the bill date in Due Clearance MIS Report ( Ascending order ) | Not Working | 13220- Critical | sajan | Prasana
Bansal | Detail / Summary in Outstanding Report | Not Working | 13209- Critical, 13210- Critical, 13211- Critical, 13212- Medium, 13213- High | sajan | Babu
Bansal | Self / "Doctor" when age above 60 the Discount should be set automatically to Senior Citizen with 10% discount | Not Working | 13214- Medium, 13215- Critical, 13216- Critical, 13217- Critical, 13218- Critical | sajan | Babu
Dar Al Hikmah | Patient wise delta and patientwise trend graph of all numeric text tests, & Picklist. (Option to view previous results with datewise column of a patient during result entry and authorization. (Revisited patient)) (Patient previous result value like Delta) | differed | Records are not saving in the bulkentry screen | sajan | Arun P
Dar Al Hikmah | Client wants in the attachment even JPEG, PNG, word file attachment option. | Not Working | 13219- Critical | sajan | Babu
Customer | Item Description | Retest Status | Resolved Bug IDs | QA Resource | Resource
Bansal | MIS Report Link has to be removed from Main Link | Done | 13181- High- reopen- For DAH link is not showing | sajan | Senthil D
Bansal | Sorting option Name, VisitID, doctor name in Service wise Transaction report | Done | 13194- High- Reopen- Something went wrong | sajan | Prasana
Dar Al Hikmah | External VisitID needs to show in Transaction Detail MIS Report | Done | 13183- Closed, 13184 (Closed) | sajan | Prasana

## 6th
Customer | Item Description | Resource | Open Bug IDs | Resource | QA Resource
Bansal | Refund cancel the record cancelled today is showing only when clicked this week ( vist is done last week). It has to be based on transaction date and not bill date. | Working with issues | 13221- High, 13222- High | Dinesh | Sajan
Bansal | Department as column to be included in the Service wise Transaction report | Not Working | 13223- Critical, 13224- High, 13225- Medium, 13226-Critical | Saravanan/Dinesh | Sajan
Bansal | Master Report - Club 4 to 5 reports and print in single go | Not Working | 13227- high, 13228- medium, 13229- critical 13230- high, 13231-High, 13232- Critical, 13233- medium, 13234- critical | Senthil D | Sajan
Bansal | Previliage Card | Not Working | 13239, 13240, 13241, 13242, 13243, 13244, 13245, 13246, 13247, 13248, 13249, 13250, 13251, 13252, 13253, 13254, 13255, 13256, 13257, 13258 | Ariharan | Sajan
Transcare | TDS clearance MIS report required. Once cleared from this window. it should reflect in User MIS Dashboard just the way "Due Clearance" reflects for complete accounting. | Not Working | 13235- High, 13236- Critical, 13237- High, 13238- High | Prasana | Sajan
Customer | Item Description | Resource | Resolved Bug IDs | Resource | QA Resource
Bansal | Sorting option Name, VisitID, doctor name in Service wise Transaction report | Done | 13194- High- Closed | Prasana | Sajan
Bansal | In User wise report collection report - Previous Due Amount break up is needed ( Format provided ) | Done | 13195- High- Closed | Babu | Sajan
Bansal | Discount Report should have same structure/format like Outstanding report | Done | 13205- Critical- Closed, 13206-High- Closed | Babu | Sajan
Makashir | "Need following columns in Home Collection Charges Report 1. Gross Amount 2. Discount Amount 3. Net Amount 4. Due Amount 5. Area 6. Due Clear Date Add filter on the top for Due Clear Date as well" | Done | 13170- Low- Closed, 13171- Critical-Closed, 13172- Critical-open- need to disscuss, 13173- Criticall (Not Issue ,Only Due Collect Amount)-open- need to disscuss,, 13174- High-Reopen, 13176- Critical (Not Issue,Register Patients only Show in Report)- Closed | Babu | Sajan
Makashir | Need the ability to download the Home Collection Charges Report (both Summary and Detail tabs) to PDF and Excel. The exported data should with the filters applied. | Done | 13175- high- Closed | Babu | Sajan
Makashir | While creating a direct GRN, the price of the items which is entered in the master data should be non-editable. However, sometimes the actual price the items come at ,can vary (near-expiry discount, promotional discount, price hike etc.). So the person who receives the goods should be able to enter the actual price the goods came at also. On the GRN PDF, I would like to see both prices for each item - the price in the master data and the actual price the item came at. Similarly, I want to see these both prices on the GRN Tracking screen as well. | Done | 13182- Critical- Closed, 13183- Critical- Closed | Babu | Sajan

## 7th
Customer | Item Description | QA status | Open Bug IDs | Resource | QA Resource
Bansal | All Option in Service wise transaction report | Not working | 13266- critical, 13267- critical, 13268- critical, 13269- Critical | Saravanan/Dinesh | Sajan
Dar Al Hikmah | Additional info needed in PCR attached file, i.e. one more column with test name should be provided. (PCR Worklist test name should have to add) | Not working | 13262- Critical, 13263- Critical | Babu | Sajan
All | Normal work flow | Normal | 13264- High, 13265- critical- Closed
Customer | Item Description | QA status | Resolved Bug IDs | Resource | QA Resource
Bansal | Page 2 is not loading when record is saved in page 2 on reloading page 1 gets loaded in Result Entry Patient List | Done | 13187- High- Closed 13188- High- Closed | Arun P | Sajan
Bansal | Thyroid has to be both Numeric and Text as some data will come with < or > symbol, delta has to be introduced for this cases as well. | Done | 13189- High- Closed, 13190- High- Closed | Arun P | Sajan
Bansal | Label Printing at both test level and department level in Patient list and dispatch | Done | 13207- High- Closed | Senthil D | Sajan
Bansal | Refund cancel the record cancelled today is showing only when clicked this week ( vist is done last week). It has to be based on transaction date and not bill date. | Done | 13221- High- Closed, 13222- High- Closed, 13270- High- new | Dinesh | Sajan
Bansal | Bill No or Branch Code column in the Bulk Entry List and Bulk Entry Screen | Done | 13191- Critical-Closed, 13192- Critical- Closed, 13193- Low- Reopen | Arun P | Sajan
Bansal | MIS Report Link has to be removed from Main Link | Done | 13181- High- Closed | Senthil D | Sajan
Bansal | Department as column to be included in the Service wise Transaction report | Done | 13223- Critical-Closed, 13224- High-Closed, 13225- Medium- Reopen- Defult not showing, 13226-Critical- Reopen- Still PDf not showing Department details | Saravanan/Dinesh | Sajan
Bansal | Comprehensive Status Report - Sample collected should not show for Radiology - "InProcess" | Done | 13208- Critical- Closed, 13271-new,13272-New | Dinesh | Sajan
Bansal | Master Report - Club 4 to 5 reports and print in single go | Done | 13231-High (Not an Issue)- Closed ,13233- medium- Closed, 13227- high- Closed, 13228- medium- Closed, 13229-Closed 13230-Closed 13232-Reopen-still something went wrong showing, 13234-Closed | Senthil D | Sajan
Bansal | Discount MIS Report - Gross amount is not shown properly. It is Showing wrong data | Done | 13180- Critical- Closed- Check with suresh | Saravanan | Sajan
Bansal | Detail / Summary in Outstanding Report | Done | 13209- Critical- Closed, 13210- Critical- Reopen- now no records found alert is showing but records are available on the grid, 13211- Critical- Closed, 13212- Medium- reopen, 13213- High- Closed | Babu | Sajan
Bansal | Report Generated on 05/02/2020 - Rename to Report Date 05/02/2020 | Done | 13197-High- Closed, 13198- Critical- Closed, 13199-Critical- Closed | Prasana | Sajan
Bansal | On Click of the Visit ID for each patient, the service details has to be shown in Outstanding Report | Done | 13196- Medium- Closed | Arun P | Sajan
Bansal | Self / "Doctor" when age above 60 the Discount should be set automatically to Senior Citizen with 10% discount | Done | 13214- Medium-Reopen- After selecting services mandatory fields are not highlighte, 13215- Critical-Now due senior citizen patient not showing in the due clearance grid, 13217- Critical- Closed, 13218- Critical- Closed | Babu | Sajan
Dar Al Hikmah | Patient wise delta and patientwise trend graph of all numeric text tests, & Picklist. (Option to view previous results with datewise column of a patient during result entry and authorization. (Revisited patient)) (Patient previous result value like Delta) | Done | 13259 - Critical- reopen-still not showing in the popup , 13260 (Closed), 13261 (Critical)- reopen-still not hsowing in the grid | Arun P | Sajan
Dar Al Hikmah | Client wants in the attachment even JPEG, PNG, word file attachment option. | Done | 13219- Critical- Closed | Babu | Sajan
Labcorp | In Technician, Authorisation & Dispatch Role- Filter Required Time wise based on registration | Done | 13166- High- Closed, 13167- high- reopen | Arun P | Sajan
Makashir | "Need following columns in Home Collection Charges Report 1. Gross Amount 2. Discount Amount 3. Net Amount 4. Due Amount 5. Area 6. Due Clear Date Add filter on the top for Due Clear Date as well" | Done | 13172- Critical (Discuss)-Closed, 13173- Critical (Discuss)- Reopen- Due patient not showing in the due clearance screen, 13174- High- open-Sunday need to test | Babu | Sajan
Makashir | Need the ability to download the Home Collection Charges Report (both Summary and Detail tabs) to PDF and Excel. The exported data should with the filters applied. | Done | 13175- high (Already closed)- Closed | Babu | Sajan
Transcare | TDS clearance MIS report required. Once cleared from this window. it should reflect in User MIS Dashboard just the way "Due Clearance" reflects for complete accounting. | Done | 13235- High-Closed, 13236- Critical-Closed, 13237- High- Closed, 13238- High- Closed | Prasana | Sajan
Trident | PHC MIS report need to add few more group test same as the existing excel format-Groups are LFT,TFT and HBA1C-Format has been shared in mail | Done | 13178- Medium- closed, 13179-closed | Saravanan | Sajan
DDC | Service Quantity needs to show in Transaction Detail MIS Report | Done | 13185- High-reopen- Excel is not genrated- we need to check in excel | Prasana | Sajan
Bansal | Advance Transaction Report,User MIS Report,Collection MIS Report,Discount MIS Report,Service Wise Transaction Report | Done | 13199-Critical-Closed, 13200- Criticalreopen-Still something went wrong showing, 13201- High-reopen- Still faceingsame issue, 13202- Critical-reopen-Date showing wrong, 132003- Critical-reopen-still facing same issue in ad MIS report , 13204- Reopen- now something went wrong alert is showing | Saravanan/Dinesh | Sajan
Product | Normal Flow | Done | 13164- Medium- reopen-still its not showing, 13177- High-Closed, 13186-High- reopen- due patinet not showing in due screen | Dinesh | Sajan

## 8th
Customer | Item Description | QA status | Open Bug IDs | Resource | QA Resource
Bansa | In outstanding Report - Credit client outstanding Included | Working |  | Babu
Customer | Item Description | QA status | Resolvled Bug IDs | Resource | QA Resource
Bansal | Refund cancel the record cancelled today is showing only when clicked this week ( vist is done last week). It has to be based on transaction date and not bill date. | Done | 13270- High- new-reopen | Dinesh
Bansal | Bill No or Branch Code column in the Bulk Entry List and Bulk Entry Screen | Done | 13193- Low- Reopen-closed | Arun P
Bansal | All Option in Service wise transaction report | Done | 13266- critical- Closed, 13267- critical- Closed, 13268- critical- Closed, 13269- Critical- Closed | Saravanan/Dinesh
Bansal | Comprehensive Status Report - Sample collected should not show for Radiology - "InProcess" | Done | 13271-new- closed, 13272-New-closed | Dinesh
Bansal | Master Report - Club 4 to 5 reports and print in single go | Done | 13232-Reopen-Closed | Senthil D
Bansal | Detail / Summary in Outstanding Report | Done | 13210- Critical- closed- | Babu
Bansal | Self / "Doctor" when age above 60 the Discount should be set automatically to Senior Citizen with 10% discount | Done | 13214- closed,13215- Critical-closed | Babu
Dar Al Hikmah | Patient wise delta and patientwise trend graph of all numeric text tests, & Picklist. (Option to view previous results with datewise column of a patient during result entry and authorization. (Revisited patient)) (Patient previous result value like Delta) | Done | 13261 - closed, 13259 - Critical- Closed | Arun P
Dar Al Hikmah | Additional info needed in PCR attached file, i.e. one more column with test name should be provided. (PCR Worklist test name should have to add) | Done | 13262- Critical- closed,13263- Critical(Not Issue,PCR Test Name Show)- closed | Babu
Makashir | Need following columns in Home Collection Charges Report 1. Gross Amount 2. Discount Amount 3. Net Amount 4. Due Amount 5. Area 6. Due Clear Date Add filter on the top for Due Clear Date as well | Done | 13173- Critical (Discuss)- Reopen- closed | Babu
DDC | Service Quantity needs to show in Transaction Detail MIS Report | Done | 13185- High-closed- | Prasana/Saravanan
Bansal | Previliage Card | Done | 13273- closed, 13274- closed,13275- closed | Ariharan

## Issues list
S.No | Bug ID | Bug description | Status
1 | 13164 | Normal: Patient is not showing due color for Is cash client-patient on the dispatch reports screen. | Closed
2 | 13165 | Feature: Required Time filters: In all screens time fields are showing like disabled it should be enabled mode color. | Closed
3 | 13166 | Feature: Required Time filters: "To hours" filed is allowing past time comparing to "From time" on all screens. | Check
4 | 13167 | Feature: Required Time filters: From and To times filters are not working properly When we search the time with particular sec's. | Closed
5 | 13168 | Feature: Invoice new format: address details should be separated with commas and grand total font size should be increased on the invoice generation print. | Closed
6 | 13169 | Feature: Invoice new format: Visit Id is showing as LAB Id on the invoice generation New format pdf | Closed
7 | 13170 | Feature: Home collection reports MIS: grid details are not closed, grid details getting design issues for details MIS reports. | Closed
8 | 13171 | Feature: Home collection reports MIS: Home collection charges are not showing in the MIS reports when we are not selected rider name in registration screen while registering | Closed
9 | 13172 | Feature: Home collection reports MIS: Area details are not showing on the Home collection reports MIS grid and pdf and Excel. | Closed
10 | 13173 | Feature: Home collection reports MIS: Due clear date is not showing MIS grid and pdf and excel sheets on Home collection Reports When we have given a discount only in due clearance screen. | Closed
11 | 13174 | Feature: Home collection reports MIS: this week field is not working properly on Sundays on Home collection reports MIS | Open
12 | 13175 | Feature: Home collection reports MIS: Something went wrong alert is showing when no records are there on the grid | Closed
13 | 13176 | Feature: Home collection reports MIS: home collection charges are not showing on MIS after assigning the rider for home collection booking patients | Closed
14 | 13177 | UID number is showing mandatory colors in registration and patient list screens | Closed
15 | 13178 |  | Closed
16 | 13179 |  | Closed
17 | 13180 |  | Closed
18 | 13181 |  | Closed
19 | 13182 |  | Closed
20 | 13183 | Feature: External VisitID: External visit iD header is showing duplicates in excel sheet | Closed
21 | 13184 | Feature: External VisitID: External visit id details are not showing in the PDF | Closed
22 | 13185 | Feature: Service Quantity MIS: Service Quantity details are shown for grand total column also | Closed
23 | 13186 | Normal: Due Patient not shoiwng in the Due clearnce screen by defuly after serching ionly its showing | Closed
24 | 13187 | Feature: Page 2: Existing details are showing in the grid, but something went wrong alert is showing in the screen Bulk entry ROAR screen | Closed
25 | 13188 | Feature: Page 2: Existing details are showing in the grid, screen is loading on the bulk entry template screen | Closed
26 | 13189 | Feature: Delta: Delta details are not showing for result type Picklist text on the bulk entry screen | Closed
27 | 13190 | Feature: Delta: Full delta details are not showing in the bulk entry screen for existing | Closed
28 | 13191 | Feature: branch code: branch code details are not showing on the result entry demografic place | Closed
29 | 13192 | Feature: branch code: Branch code details are not showing in the bulk entry template screen | Closed
30 | 13193 | Feature: branch code: grid details are not closed completely on the bulk entry grid | Closed
31 | 13194 | Feature: sort: doctor wise details sort is not working properlly on the Service wise transation MIS reports screen | Closed
32 | 13195 | Feature: Previous Due: something went wrong alert is Showing when amount is zero on the Previous Due Amount grid. | Closed
33 | 13196 | Feature: Service details outstanding: Bill PDF icon details should be showing on the Outstanding MIS Report. | Closed
34 | 13197 | Feature: Report Date: Due clearance MIS reports Report date label name is not showing in the PDF | Closed
35 | 13198 | Feature: Report Date: (Refund Cancel MIS Report, Transaction Details MIS Report, Advanced Transaction MIS Report, Collection MIS Reports) Report generated label is showing on the PDF. | Closed
36 | 13199 | Feature: Report Date: Export to pdf is not generated on the Advanced Transaction MIS Report. | Closed
37 | 13200 | Feature: Performance tune: Something went wrong alert is shown when we search the last 6 months records export to pdf on Advanced Transaction MIS Report | Open
38 | 13201 | Feature: Performance tune: Continuously loading the last 6 months records export to pdf on Discount MIS Report | Open
39 | 13202 | Feature: Performance tune: Reporte date is showing wrong on the when we export to the 6-month records on Discount MIS Report PDF | Open
40 | 13203 | Feature: Performance tune: Something went wrong alert is shown on the all MIS reports when we search on the last 6 month records | Open
41 | 13204 | Feature: Performance tune: No records found alert is showing on the gird when we today records are available on the grid but select last 6 month records on the custom search and click on the summary or details without selecting the search icon on the discount and Outstanding reports | Open
42 | 13205 | Feature: Discount MIS reports: Discount amount is showing wrong on the grid when we give bill discount and the due discount same patient | Closed
43 | 13206 | Feature: Discount MIS reports: Something went wrong alert is shown When clicking the export excel and pdf while records are not available on the grid | Closed
44 | 13207 | Feature: Label Printing: there is no difference between visit print and demographic details print. both grid details are showing the same records. | Closed
45 | 13208 | Feature: Comprehensive Status Report: Sample collected is showing for cytology and Xray department services for that status should be "InProcess". | Closed
46 | 13209 | Feature: Outstanding MIS: default self details are shown in the summary grid and the amount is showing zero when self patients are not available on the summary gird. | Closed
47 | 13210 | Feature: Outstanding MIS: Something went wrong alert showing when we trying to export the summary details on outstanding misreport screen. | Closed
48 | 13211 | Feature: Outstanding MIS: Export pdf blank and error details are showing in the PDF when we trying the outstanding details through export the pdf. | Closed
49 | 13212 | Feature: Outstanding MIS: Unessarlly scroll bars are showing in the outstanding MIS reports screens. | Closed
50 | 13213 | Feature: Outstanding MIS: referral type filter is not working properly on the outstanding MIS reports screen. | Closed
51 | 13214 | Feature: Senior Citizen discount: mandatory fields (Approved by and remarks) are not highlighting in the registration screen. | Closed
52 | 13215 | Feature: Senior Citizen discount: without selecting discount type default senior citizen discount is loading in the due clearance screen. when senior citizen have due. | Closed
53 | 13216 | Feature: Senior Citizen discount: Discount amount is showing wrong in the bill edit screen when we have given senior citizen discount in registration and due clearance screens. | Open
54 | 13217 | Feature: Senior Citizen discount: Discount type is not changed after updating the DOB on the bill edit screen. | Closed
55 | 13218 | Feature: Senior Citizen discount: Without selecting any patient default senior citizen discount type is loading in the due clearance screen. | Closed
56 | 13219 | Feature: JPEG File upload: Uploaded document details are not opening in the bulk entry screen for PCR patient."This site can’t be reached" Alert is showing but all application is working | Closed
57 | 13220 | Feature: Due Clearance MIS Report sort: Export to PDf and Export to excel not showing in then Ascending order | Closed
58 | 13221 | Feature: refund cancel MIS: refund cancel MIS grid details are not showing clearly. grid details and grid label details are mismatching. | Closed
59 | 13222 | Feature: refund cancel MIS: search is not working properly, grid have patient details but the search is not showing that details. | Closed
60 | 13223 | Feature: Service-wise transition MIS: department wise search is not working in the Service-wise transition summary MIS. | Closed
61 | 13224 | Feature: Service-wise transition MIS: Referal type-wise search is not working on the Service-wise transition summary MIS. | Closed
62 | 13225 | Feature: Service-wise transition MIS: Summary and Details are not indicating the screen while selecting the tab details on the Service-wise transition summary MIS. | Closed
63 | 13226 | Feature: Service-wise transition MIS: PDf not showing department wise reports on the Service-wise transition summary MIS. | Closed
64 | 13227 | Feature: Master Report: records with No records found alert are showing while exporting the details on the cumulative record screen. | Closed
65 | 13228 | Feature: Master Report: export to excel name should be provided while exporting the sheet on the cumulative record screen | Closed
66 | 13229 | Feature: Master Report: blank pages are shown in between reports on the cumulative PDF reports. | Closed
67 | 13230 | Feature: Master Report: Records are not showing order wise in excel sheet on the cumulative reports. | Closed
68 | 13231 | Feature: Master Report: Custom dates are available but the search button is missing the cumulative reports. | Closed
69 | 13232 | Feature: Master Report: Something went wrong alert is showing while selecting custom details and exportin the details on the cumulative reports. | Closed
70 | 13233 | Feature: Master Report: The Branch label name is overlapping with branch details on the cumulative reports. | Closed
71 | 13234 | Feature: Master Report: branch wise details are not exporting while trying to export. nothing happening on the cumulative reports. | Closed
72 | 13235 | Feature: TDS MIS: default TDS details are not showing in the grid on TDS MIS screen. | Closed
73 | 13236 | Feature: TDS MIS: Without paying TDS that details are showing in the TDS MIS screen. | Closed
74 | 13237 | Feature: TDS MIS: TDS grand total is not showing in the EXport details and grid details on the TDS MIS Screen. | Closed
75 | 13238 | Feature: TDS MIS: Invoice payment screen is getting design issue after paying the invoice payment. | Closed
76 | 13239 | Feature: Privilege: Card start with details are not showing correctly. Card details not starting with given field details. | closed
77 | 13240 | Feature: Privilege: there is no gap between the fields, label names are overlapping with other field details. | Closed
78 | 13241 | Feature: Privilege: End date functionality is not working properly on the privilege card screen. | Closed
79 | 13242 | Feature: Privilege: flat discount option is not available on the privilege card screen. | Open-PO | need to dic
80 | 13243 | Feature: Privilege: edit icon and label name should be changed in the privilege card screen. On the screen, info is showing. | Closed
81 | 13244 | Feature: Privilege: after clicking edit valid to details are not showing on the field in privilege. | Closed
82 | 13245 | Feature: Privilege: Updated details are not showing in the grid after update the card details. | Closed
83 | 13246 | Feature: Privilege: Updated successfully alert is showing wrong while updating the card details on the privilege card screen. | Closed
84 | 13247 | Feature: Privilege: we are able to enter the paid amount details in the paid amount field on the privilege card registration screen. | Closed
85 | 13248 | Feature: Privilege: department wise discount is not working properly on the registration screen. when we give discount department wise on the privilege card screen. | Closed
86 | 13249 | Feature: Privilege: privilege card discount details are showing like service wise discount on the discount MIS report screen. | Open-PO | need to dic
87 | 13250 | Feature: Privilege: We are able to edit the discount after selecting the privilege on the registration screen. | Open-PO | need to dic
88 | 13251 | Feature: Privilege: There is no limit available for cards. More then a card payment discount is allowing the registration screen. | Open-PO | need to dic
89 | 13252 | Feature: Privilege: Without giving direct discount details it allowing to create the card on the privilege card screen. | Closed
90 | 13253 | Feature: Privilege: card inactive option is not available on the privilege card screen. | Closed
91 | 13254 | Feature: Privilege: Error print alert is showing when we click on the save print option on the privilege card registration screen. | Closed
92 | 13255 | Feature: Privilege: Mandatory fields are not highlighting on the privilege card registration screen. | Closed
93 | 13256 | Feature: Privilege: Card details showing mandatory highlighting in the registration screen for normal patients. | Closed
94 | 13257 | Feature: Privilege: we are unable to change card details on the registration screen when the patient has multiple cards. | Open-PO | need to dic
95 | 13258 | Feature: Privilege: valid to the field is allowing alphabets and special char on the privilege card screen. | Closed
96 | 13259 | Features: Delta: Patient wise delta details are not shown in the bulk entry screen when the patient has multiple records. | Closed
97 | 13260 | Features: Delta: Change the service wise delta icon position and icon also it defaults to find on the grid. | Closed
98 | 13261 | Features: Delta: Patient wise dealt si not showing in the bulk entry grid | Closed
99 | 13262 | Feature: PCR Worklist test name: ABRE and ROAR services screen test names are not showing | Closed
100 | 13263 | Feature: PCR Worklist test name: When attached attachments for the normal services and PCR services, in popup normal services test name is not showing. | Closed
101 | 13264 | Normal: online payment mode dropdown is not loading on bill edit and registration and die clearance and refund cancel screens. | Closed
102 | 13265 | Normal: ROAR result entry screen is not opening, the screen is consciously loading after patients select | Closed
103 | 13266 | Feature: All Option in Service-wise: Export to excel branch details are not showing while exporting the excel individual branch details | Closed
104 | 13267 | Feature: All Option in Service-wise: Export to PDF not showing all individual branch details it showing only one brach details for all branch export to excel pdf. | Closed
105 | 13268 | Feature: All Option in Service-wise: When we trying to export to pdf or export excel details for all branches. that details are not showing in excel and pdf. brach wise separate column is not available on excel and pdf | Closed
106 | 13269 | Feature: All Option in Service-wise: branch filters are not available for sub branch service wise transaction mis report screen | Closed
107 | 13270 | Feature: refund cancel MIS: Scroll bar is not working when more records are available on the grid | Closed
108 | 13271 | Feature: Inprocess: P should be small in Status process | Closed
109 | 13272 | Feature: Inprocess: self is showing multiple times when patients have multiple radiology department aptuents on comprehensive status MIs screen | Closed
110 | 13273 | Feature: Privilege: After entering the first name field is highlighting like a mandatory field on the privilege registration screen. | Closed
111 | 13274 | Feature: Privilege: Enter more than card amount and click on the save alerts is showing after that DOB details are clearing on the privilege registration screen. | Closed
112 | 13275 | Feature: Privilege: Card suffix field si allowing special and alphabets after saving view info not showing that card suffix details. | Closed
113 | 13276 | Feature: Privilege: Visit number and payment details are showing empty in bill print after saving the new card patients' details. | Open
114 | 13277 | Normal: without selecting discount type remark is showing a mandatory alert on due clearance screen | Closed

## 1.9.71- tested feature
S.No | Customer | Item Description | QA feature Status | Open issues | Closed issues | Resource | Development Status | QA Resource
1 | Bansal | The Default branch option once login should not come even after save clicked | Working |  |  | Senthil D | Completed | Sajan
2 | Bansal | Page 2 is not loading when record is saved in page 2 on reloading page 1 gets loaded in Result Entry Patient List | Working |  | 13187- High, 13188- High | Arun P | Completed | Sajan
3 | Bansal | When complete option is clicked in the Bulk entry list, only the first page complete records are shown it has to show overall complete records not only first page completed records | Working |  |  | Arun P | Completed | Sajan
4 | Bansal | Thyroid has to be both Numeric and Text as some data will come with < or > symbol, delta has to be introduced for this cases as well. | Working |  | 13189- High- Closed, 13190- High- Closed | Arun P | Completed | Sajan
5 | Bansal | Label Printing at both test level and department level in Patient list and dispatch | Partially tested- Working |  | 13207- High- Closed | Senthil D | Yet to Start | Sajan
6 | Bansal | Refund cancel the record cancelled today is showing only when clicked this week ( vist is done last week). It has to be based on transaction date and not bill date. | Working |  | 13221- High- Closed, 13222- High- Closed, 13270- High- reopen | Saravanan/Dinesh | Completed | Sajan
7 | Bansal | Bill No or Branch Code column in the Bulk Entry List and Bulk Entry Screen | Working |  | 13191- Critical-Closed, 13192- Critical- Closed, 13193- Low | Arun P | Completed | Sajan
8 | Bansal | MIS Report Link has to be removed from Main Link | Working |  | 13181- High- Closed | Senthil D | Completed | Sajan
9 | Bansal | Calendar control instead of the current control in the MIS reports | Working |  |  | Senthil D | Completed | Sajan
10 | Bansal | Sorting option Name, VisitID, doctor name in Service wise Transaction report | Working |  | 13194- High | Prasana | Completed | Sajan
11 | Bansal | Department as column to be included in the Service wise Transaction report | Working |  | 13223- Critical-Closed, 13224- High-Closed, 13225- Medium, 13226-Critical | Saravanan/Dinesh | Completed | Sajan
12 | Bansal | Comprehensive Status Report - Sample collected should not show for Radiology - "InProcess" | Working |  | 13208- Critical- Closed, 13271-new,13272-New | Dinesh | Completed | Sajan
13 | Bansal | In User wise report collection report - Previous Due Amount break up is needed ( Format provided ) | Working | pdf not opeing in my system | 13195- High | Babu | Completed | Sajan
14 | Bansal | Master Report - Club 4 to 5 reports and print in single go | Working |  | 13231-High (Not an Issue)- Closed ,13233- medium- Closed, 13227- high- Closed, 13228- medium- Closed, 13229-Closed 13230-Closed 13234-Closed, 13232-Closed | Senthil D | Completed | Sajan
15 | Bansal | Discount MIS Report - Gross amount is not shown properly. It is Showing wrong data | Working |  | 13180- Critical | Saravanan | Completed | Sajan
16 | Bansal | Sort the report based on the bill date in Due Clearance MIS Report ( Ascending order ) | Working |  |  | Prasana | Completed | Sajan
17 | Bansal | Detail / Summary in Outstanding Report | Working |  | 13209- Critical- Closed, 13211- Critical- Closed, 13212- Medium- reopen, 13213- High- Closed, 13210- Critical- closed- | Babu | Completed | Sajan
18 | Bansal | Report Generated on 05/02/2020 - Rename to Report Date 05/02/2020 | Working |  | 13197-High- Closed, 13198- Critical- Closed, 13199-Critical- Closed | Prasana | Completed | Sajan
19 | Bansal | On Click of the Visit ID for each patient, the service details has to be shown in Outstanding Report | Working |  | 13196- Medium- Closed | Arun P | Completed | Sajan
20 | Bansal | Self / "Doctor" when age above 60 the Discount should be set automatically to Senior Citizen with 10% discount | Working With issue | 13216- Critical | 13217- Critical- Closed, 13218- Critical- Closed, 13215- Critical,13214- closed,13215- Critical-closed | Babu | Yet to Start | Sajan
21 | Bansal | Discount Report should have same structure/format like Outstanding report | Working |  | 13205- Critical, 13206-High | Babu | Completed | Sajan
22 | CDC | OUTSTANDINGREPORT-Export to pdf option required | Working |  | 13163- Critical, | Babu | Completed | Sajan
23 | Dar Al Hikmah | Patient wise delta and patientwise trend graph of all numeric text tests, & Picklist. (Option to view previous results with datewise column of a patient during result entry and authorization. (Revisited patient)) (Patient previous result value like Delta) | Working |  | 13260 (Closed), 13261- Critical, 13259- Critical, | Arun P | Completed | Sajan
24 | Dar Al Hikmah | Invoice new format (DAH has to provide the format)..Invoice format need to be changed as per given format | Working |  | 13168- Medium, 13169- Critical | Arun P | Completed | Sajan
25 | Dar Al Hikmah | Client wants in the attachment even JPEG, PNG, word file attachment option. | Working |  | 13219- Critical- Closed | Babu | Completed | Sajan
26 | Labcorp | In Technician, Authorisation & Dispatch Role- Filter Required Time wise based on registration | Working |  | 13165- medium,13167- High- Closed, 13166- high- | Arun P | Completed | Sajan
27 | Makashir | "Need following columns in Home Collection Charges Report 1. Gross Amount 2. Discount Amount 3. Net Amount 4. Due Amount 5. Area 6. Due Clear Date Add filter on the top for Due Clear Date as well" | Working With issue | 13174- High- Sunday need to test | 13170- Low- Closed, 13171- Critical-Closed, 13176- Critical,13172- Critical (Discuss)-Closed, 13173- Critical, 13173- | Babu | Completed | Sajan
28 | Makashir | Need the ability to download the Home Collection Charges Report (both Summary and Detail tabs) to PDF and Excel. The exported data should with the filters applied. | Working |  | 13175- high (Already closed)- Closed | Babu | Completed | Sajan
29 | Makashir | While creating a direct GRN, the price of the items which is entered in the master data should be non-editable. However, sometimes the actual price the items come at ,can vary (near-expiry discount, promotional discount, price hike etc.). So the person who receives the goods should be able to enter the actual price the goods came at also. On the GRN PDF, I would like to see both prices for each item - the price in the master data and the actual price the item came at. Similarly, I want to see these both prices on the GRN Tracking screen as well. | Working |  | 13182- Critical, 13183- Critical | Babu | Completed | Sajan
30 | Product | Previliage Card | Working With issue | 13242-PO, 13249-PO, 13250-PO, 13251-PO, 13252-PO, 13254-PO, 13257-PO, 13276- New | 13239, 13240, 13241, 13243, 13244, 13245, 13246, 13247, 13248, 13253, 13255, 13256, 13258,13273-New, 13274- new, 13275- new, | Ariharan | Yet to Start | Sajan
31 | Transcare | TDS clearance MIS report required. Once cleared from this window. it should reflect in User MIS Dashboard just the way "Due Clearance" reflects for complete accounting. | Working |  | 13235- High-Closed, 13236- Critical-Closed, 13237- High- Closed, 13238- High- Closed | Dinesh | Completed | Sajan
32 | Trident | PHC MIS report need to add few more group test same as the existing excel format-Groups are LFT,TFT and HBA1C-Format has been shared in mail | Working |  | 13178- Medium- closed, 13179-closed | Saravanan | Completed | Sajan
33 | Dar Al Hikmah | External VisitID needs to show in Transaction Detail MIS Report | Working |  | 13183- High, 13184- High | Prasana | Completed | Sajan
34 | DDC | Service Quantity needs to show in Transaction Detail MIS Report | Working |  | 13185- Medium | Prasana | Completed | Sajan
35 | Bansal | Discount MIS Report, Advanced Transaction MIS Report, User MIS Report, Collection MIS Reports, Service Wise Summary MIS Report. | Notworking | 13200- Critical, 13201- High, 13202- Critical, 132003- Critical, 13204- High, | 13199-Critical-Closed, | Suresh |  | Sajan
36 | Bansal | All Option in Service wise transaction report | Working |  | 13266- critical- Closed, 13267- critical- Closed, 13268- critical- Closed, 13269- Critical- Closed | Saravanan/Dinesh | Completed | Sajan
37 | Dar Al Hikmah | Additional info needed in PCR attached file, i.e. one more column with test name should be provided. (PCR Worklist test name should have to add) | Working |  | 13262- Critical, 13263- Critical | Babu | Completed | Sajan
38 | All | Normal work flow | Working |  | 13177- High-Closed, 13265- critical- Closed, 13186-High,13164- Medium-Closed, 13264- High-Closed, 13277- High- Closed |  | Completed | Sajan
39 | Bansa | In outstanding Report - Credit client outstanding Included | Working |  |  | Babu | Completed | Sajan